## Sheet1
Date | Task
17/11/23 - 23/11/23 | Database schema and data migration scripts and documenation
ReactJS application with user interface components
24/11/23 - 30/11/23 | Unit tests for backend components
Routing and navigation between different pages
1/12/23 - 7/12/23 | Integration with backend APIs for data fetching and manipulation
8/12/23 - 14/12/23 | Spring Boot application with RESTful APIs
15/12/23 - 20/12/23 | Documentation finalisation